## Test Execution
Task ID | Task Description | Page Name(s) | Page URL(s) | Initial Publishing Status | Action Performed | Scheduled Publish (IST) | Scheduled Unpublish (IST) | Original Schedule Time | Updated Schedule Time | Actual Execution Time | Expected Result | Actual Result | EMA Actions & Observations | Integration / API Interactions | Changes Made During Testing | Verification Result | Supporting Evidence | Issues / Errors / Limitations | Manual Intervention Required | Final Status
T1 | Schedule an unpublished page for publishing; verify it goes live at the scheduled time with the latest (previewed) content. | beervana-portland | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/beervana-portland | Unpublished (preview 200 @ 16 Oct 2026 15:36 IST; live 404) | Schedule publish via crontab (/.helix/crontab) | 19 Oct 2026 16:00 IST (10:30 UTC) | N/A | 16:00 IST | N/A | 19 Oct 2026 16:00:04 IST (live.lastModified) — ~4 s after scheduled time | Page live status 200 after 16:00 IST tick; live content == preview; audit evidence of publish. | Live 200 from 16:00:04 IST; live content identical to latest preview; indexer + sitemap entries at 16:00:14-16 IST. | Created crontab v1 (15:46 IST); polled status every 20s from 15:56 IST; compared live vs preview .plain.html; read audit log. | Status API, aem.live CDN, aem.page, Audit Log API — all 200. | Created /.helix/crontab with 1 row. | Passed | status live.lastModified=16:00:04 IST; aem.live 200; content match true (7033 B); audit log: indexer added page 16:00:14 IST, sitemap (system) 16:00:16 IST | Audit log has no explicit route=live entry for the scheduler-run publish; only downstream indexer/sitemap entries (user system). | None | Passed
T2 | Schedule an unpublished page for publishing, then cancel the schedule before it fires; verify page stays unpublished past the original time. | napa-wine-tasting | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/napa-wine-tasting | Unpublished (preview 200; live 404) | Schedule publish, then cancel before it fires | 16:10 IST (10:40 UTC) — to be cancelled | N/A | 16:10 IST | N/A | No execution (cancelled) — page still unpublished at 16:13:32 IST, 3.5 min after original 16:10 time | Page stays unpublished after the original 16:10 IST time; no publish evidence. | live 404 on all polls 16:09:47-16:13:32 IST; aem.live 404; no audit-log activity for the page. | Added row (v2, 15:47), removed row (v3, 15:51, after 15:50 tick), polled status through 16:10 tick. | DA source POST 200; preview POST 200 | Crontab v2: +1 row; v3: row removed | Passed | Status API live 404 (no live.lastModified) on all polls 16:09:47-16:13:32 IST; aem.live HTTP 404; no audit-log activity for the page. Final snapshot 16:46:18 IST: still live 404 (36 min after original time). | None | None | Passed
T3 | Schedule an unpublished page, then change the schedule to a different future time; verify it publishes at the updated time, not the original. | tahoe-skiing | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/tahoe-skiing | Unpublished (preview 200; live 404) | Schedule publish, then change time | 16:20 IST (10:50 UTC) — updated from 16:10 IST | N/A | 16:10 IST (10:40 UTC) | 16:20 IST (10:50 UTC) | 19 Oct 2026 16:20:04 IST (live.lastModified) — updated time; did NOT run at original 16:10 | Not live after original 16:10 IST; live after updated 16:20 IST. | live 404 through 16:19:51 IST (incl. 16:10 tick); live 200 from 16:20:04 IST; content identical to preview. | Crontab v2 (15:47) original 10:40 UTC; v3 (15:51) changed to 10:50 UTC; polled through 16:10 and 16:20 ticks; compared live vs preview. | DA source POST 200; preview POST 200 | Crontab v2: +1 row; v3: time 10:40 -> 10:50 UTC | Passed | 16:10 tick: live 404 (polls 16:09:47-16:13:32 IST). 16:20 tick: live.lastModified 16:20:04 IST, aem.live 200, content match true (4427 B). Audit: indexer added page 16:20:35 IST, sitemap 16:20:36 IST. | Audit-log entry visible only after ingestion delay (O2). | None | Passed
T4 | Bulk-schedule multiple unpublished pages for publishing at one future time; verify each page individually. | guide-la-skateparks, san-diego-surf, ski-touring, western-australia | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/{guide-la-skateparks¦san-diego-surf¦ski-touring¦western-australia} | All 4 unpublished (preview 200; live 404) at 15:51:57 IST snapshot | Bulk schedule publish (one crontab row, 4 line-feed separated commands) | 16:25 IST (10:55 UTC) | N/A | 16:25 IST | N/A | guide-la-skateparks 16:25:04 · san-diego-surf 16:25:05 · ski-touring 16:25:06 · western-australia 16:25:06 IST | All 4 pages live after 16:25 IST tick. | 4/4 live 200 within 2 s of each other; content identical to preview for each. | Crontab v5 (15:55): single multi-command row. Polled all 4 through the 16:25 tick; compared live vs preview per page; read audit log. | DA source POST 200; preview POST 200 (no x-error) | Crontab v5: +1 row (4 commands) | Passed (4/4) | PER PAGE — guide-la-skateparks: live 200, lastModified 16:25:04, match (7259 B) ¦ san-diego-surf: live 200, 16:25:05, match (7607 B) ¦ ski-touring: live 200, 16:25:06, match (8571 B) ¦ western-australia: live 200, 16:25:06, match (11843 B). Audit: one indexer entry 16:25:14 IST listing all 4 as added. | None | None | Passed
T5 | Schedule a page to publish at a future time and unpublish at a later time; verify both. | arctic-surfing | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/arctic-surfing | Unpublished (preview 200; live 404) | Schedule publish + later unpublish via crontab | 16:25 IST (10:55 UTC) | 16:40 IST (11:10 UTC) | Publish 16:25 IST / Unpublish 16:40 IST | N/A | Publish: 16:25:04 IST (live.lastModified). Unpublish: on the 16:40 IST tick — indexer deletion logged 16:40:14 IST (exact unpublish second Not Verified; Status API keeps no live timestamp after unpublish) | Live 200 after 16:25 IST; live 404 after 16:40 IST; both rows saved. | Both rows saved (readback + activation 200). Live 200 at 16:25:04 and still 200 at 16:35:00 IST; live 404 from 16:40:53 IST on every poll; indexer deleted page 16:40:14 IST. | Crontab v4 (15:53) +2 rows; polled through 16:25 and 16:40 ticks; compared live vs preview after publish; checked audit log and live query-index. | DA source POST 200; preview POST 200 (no x-error) | Crontab v4: +2 rows | Passed (publish + unpublish) | Publish — live.lastModified 16:25:04 IST; aem.live 200; content match (10128 B); indexer added 16:25:14 IST. Unpublish — status live 404; aem.live 404; indexer "content: deleted" 16:40:14 IST; sitemap 16:40:15 IST; not in query-index.json. | Exact unpublish time not directly observable (no live.lastModified after unpublish); bounded by 16:35:00 (live) and 16:40:14 IST (index deletion). | None | Passed

## Activity Log
# | Timestamp (IST) | Task | Actor | Action | Details | Result
1 | 19/10/2026, 15:29:49 IST | Setup | EMA | Checked current time | Current time 15:26 IST (09:56 UTC), 19 Oct 2026 | OK
2 | 19/10/2026, 15:29:49 IST | Setup | EMA | Read-only discovery: listed DA content | GET admin.da.live/list (recursive): 28 documents | OK
3 | 19/10/2026, 15:29:50 IST | Setup | EMA | Read-only discovery: page status snapshot | GET admin.hlx.page/status for all 28 docs: 11 published (incl. nav/footer), 17 unpublished (preview 200, live 404). Preview is newer than DA source for all unpublished pages, so preview = latest content. | OK
4 | 19/10/2026, 15:29:50 IST | Setup | EMA | Identified scheduler mechanism | AEM scheduler = crontab sheet at /.helix/crontab (UTC times, 5-min ticks, activated by preview). Checked: no crontab exists (DA 404, preview 404). Snapshots: none. Publish jobs: none. Audit log last 1h: empty. | OK
5 | 19/10/2026, 15:29:50 IST | Setup | EMA | Created testing log | scheduler-test-log.xlsx with tabs: Test Execution, Activity Log, Scheduling Changes, Integrations, Issues & Limitations, Final Summary, Page Inventory (Initial) | OK
6 | 19/10/2026, 15:29:51 IST | Setup | EMA | Proposed timeline sent to user | Awaiting approval of plan and Task 1 page selection. No state-changing actions taken. | Awaiting user
7 | 19/10/2026, 15:32:49 IST | Setup | User | Approved testing plan & timeline | Parallel execution plan approved (T1 16:00, T2/T3 16:10→16:20, T4/T5 16:25, T5 unpublish 16:40 IST) | Approved
8 | 19/10/2026, 15:32:50 IST | T1 | User | Selected page for Task 1 | /us/en/adventures/beervana-portland | Approved
9 | 19/10/2026, 15:45:42 IST | T1 | User | Approved T1 schedule | Create /.helix/crontab; publish beervana-portland at 16:00 IST (10:30 UTC) | Approved
10 | 19/10/2026, 15:45:49 IST | T2 | User | Selected page for Task 2 | /us/en/adventures/napa-wine-tasting | Approved
11 | 19/10/2026, 15:45:50 IST | T3 | User | Selected page for Task 3 | /us/en/adventures/tahoe-skiing | Approved
12 | 19/10/2026, 15:46:23 IST | T1 | EMA | Created crontab sheet in DA | POST admin.da.live/source/.../.helix/crontab.json -> HTTP 200 (1st attempt: client-side tool error, no response; retried). Readback matches: when='at 10:30 am on the 19th day of October in 2026', command='publish /us/en/adventures/beervana-portland' | OK
13 | 19/10/2026, 15:46:23 IST | T1 | EMA | Activated schedule (preview crontab) | POST admin.hlx.page/preview/.../.helix/crontab.json -> HTTP 200, no x-error; preview lastModified 19 Oct 2026 15:46:09 IST, lastModifiedBy araji@adobe.com. Public URL of /.helix/crontab.json returns 404 (system path, not served) - expected. | OK
14 | 19/10/2026, 15:47:08 IST | T2 | User | Approved T2 schedule | napa-wine-tasting publish at 16:10 IST (10:40 UTC) | Approved
15 | 19/10/2026, 15:47:08 IST | T3 | User | Approved T3 schedule (original time) | tahoe-skiing publish at 16:10 IST (10:40 UTC) | Approved
16 | 19/10/2026, 15:47:28 IST | T2/T3 | EMA | Updated crontab to v2 and re-activated | DA POST 200; readback shows 3 rows (T1 10:30 UTC, T2 10:40 UTC, T3 10:40 UTC). Preview POST 200, no x-error, lastModified 15:47:19 IST. | OK
17 | 19/10/2026, 15:48:40 IST | T2 | User | Approved cancellation of T2 schedule | Remove napa-wine-tasting 16:10 IST row after 15:50 IST tick | Approved
18 | 19/10/2026, 15:48:40 IST | T3 | User | Approved T3 reschedule | tahoe-skiing 16:10 IST -> 16:20 IST (10:50 UTC) | Approved
19 | 19/10/2026, 15:51:23 IST | T2/T3 | EMA | Checked audit log after 15:50 IST tick | admin.hlx.page/log since 15m: only 2 entries (crontab previews at 15:46:07 and 15:47:18 IST by araji@adobe.com). No scheduler-run entries recorded (none expected yet). | OK
20 | 19/10/2026, 15:51:24 IST | T2/T3 | EMA | Updated crontab to v3 and re-activated | Removed napa-wine-tasting row (T2 cancel); changed tahoe-skiing row 10:40 -> 10:50 UTC (T3). DA POST 200; readback shows 2 rows. Preview POST 200, no x-error, lastModified 15:51:13 IST. | OK
21 | 19/10/2026, 15:52:22 IST | T4 | User | Approved read-only Task 4 snapshot |  | Approved
22 | 19/10/2026, 15:52:22 IST | T5 | User | Selected page for Task 5 | /us/en/magazine/arctic-surfing | Approved
23 | 19/10/2026, 15:52:23 IST | T4 | EMA | Took snapshot of unpublished pages (read-only) | Status API for 28 docs at 15:51:57 IST: 17 unpublished (live 404), 11 published - unchanged from baseline. Excluding T1/T2/T3/T5 pages (beervana-portland, napa-wine-tasting, tahoe-skiing, arctic-surfing) leaves 13 candidates: climbing-new-zealand, downhill-skiing-wyoming, gastronomic-marais-tour, riverside-camping-australia, ski-touring-mont-blanc, surf-camp-costa-rica, west-coast-cycling, whistler-mountain-biking, yosemite-backpacking, magazine/guide-la-skateparks, magazine/san-diego-surf, magazine/ski-touring, magazine/western-australia | OK
24 | 19/10/2026, 15:53:23 IST | T4 | User | Selected bulk pages | All 4 magazine pages: guide-la-skateparks, san-diego-surf, ski-touring, western-australia | Approved (pages only; schedule approval pending)
25 | 19/10/2026, 15:53:24 IST | T5 | User | Approved T5 schedules | Publish 16:25 IST (10:55 UTC); unpublish 16:40 IST (11:10 UTC) | Approved
26 | 19/10/2026, 15:53:42 IST | T5 | EMA | Updated crontab to v4 and re-activated | Added arctic-surfing publish 10:55 UTC and unpublish 11:10 UTC. DA POST 200; readback shows 4 rows. Preview POST 200, no x-error, lastModified 15:53:35 IST. | OK
27 | 19/10/2026, 15:55:27 IST | T4 | User | Approved T4 bulk schedule | 4 magazine pages, one multi-command row, 16:25 IST (10:55 UTC) | Approved
28 | 19/10/2026, 15:55:45 IST | T4 | EMA | Updated crontab to v5 and re-activated | Added 1 multi-command row (4 publish lines, line-feed separated) at 10:55 UTC. DA POST 200; readback shows 5 rows incl. the multi-line cell. Preview POST 200, no x-error, lastModified 15:55:39 IST. | OK
29 | 19/10/2026, 16:01:22 IST | T1 | User | Approved T1 verification | Wait in-session for 16:00 IST run | Approved
30 | 19/10/2026, 16:01:22 IST | T1 | EMA | Polled page status (every ~20s, 15:56:27-16:00:12 IST) | live 404 through 15:59:51 IST; live 200 at 16:00:12 IST poll | Live
31 | 19/10/2026, 16:01:22 IST | T1 | EMA | Verified publish evidence | Admin status: live 200, live.lastModified 19 Oct 2026 16:00:04 IST. aem.live HTTP 200; live .plain.html byte-identical to preview (7033 B). Audit log: indexer 'content: added /us/en/adventures/beervana-portland' 16:00:14 IST; sitemap updated by 'system' 16:00:16 IST; query-index POST by 'system' 16:00:14 IST. No user-initiated /live call in the log (EMA made none). | Passed
32 | 19/10/2026, 16:02:42 IST | T2/T3 | User | Approved 16:10 IST checks | Wait in-session | Approved
33 | 19/10/2026, 16:13:46 IST | T2/T3 | EMA | Polled napa-wine-tasting & tahoe-skiing through 16:10 IST tick (16:09:47-16:13:32 IST, every ~20s) | Both live 404 on every poll. aem.live HTTP 404 for both. Audit log: no new entries after 16:00:16 IST (no indexer/sitemap activity for either page). | Both unpublished
34 | 19/10/2026, 16:16:00 IST | T3 | User | Approved T3 verification (T3 only) | Wait in-session for 16:20 IST run | Approved
35 | 19/10/2026, 16:21:00 IST | T3 | EMA | Polled tahoe-skiing through 16:20 IST tick (16:19:30-16:20:11 IST) | live 404 at 16:19:30 & 16:19:51; live 200 at 16:20:11 poll. Status live.lastModified 16:20:04 IST. aem.live 200; live .plain.html identical to preview (4427 B). Audit log (since 16:12:49 IST) checked at 16:20:49 IST: no entries yet (indexer entry seen for T1 not present for T3). | Passed
36 | 19/10/2026, 16:21:42 IST | T4/T5 | User | Approved 16:25 IST verification | T4 bulk pages + T5 publish | Approved
37 | 19/10/2026, 16:26:18 IST | T4/T5 | EMA | Polled 5 pages through 16:25 IST tick (16:24:31-16:25:12 IST) | All 5 live 404 at 16:24:31 & 16:24:52; all 5 live 200 at 16:25:12 poll. | Live
38 | 19/10/2026, 16:26:18 IST | T4/T5 | EMA | Verified publish evidence per page | live.lastModified IST: guide-la-skateparks 16:25:04, san-diego-surf 16:25:05, ski-touring 16:25:06, western-australia 16:25:06, arctic-surfing 16:25:04. aem.live 200 and content identical to preview for all 5 (7259/7607/8571/11843/10128 B). Audit log: indexer 16:25:14 IST 'content: added' for all 5 pages; sitemap (system) 16:25:16 IST. | Passed
39 | 19/10/2026, 16:26:19 IST | T3 | EMA | Re-checked audit log | Indexer entry 'content: added /us/en/adventures/tahoe-skiing' at 16:20:35 IST and sitemap 16:20:36 IST now present - earlier 16:20:49 query did not return them (log ingestion lag). | Evidence added
40 | 19/10/2026, 16:26:51 IST | T5 | User | Approved T5 unpublish verification | Wait in-session for 16:40 IST run | Approved
41 | 19/10/2026, 16:42:43 IST | T5 | EMA | Polled arctic-surfing through 16:40 IST tick | Pre-check 16:35:00 IST: live 200. Polls 16:40:53-16:42:14 IST: live 404 on every poll. (Poll lines between 16:39:30 and 16:40:53 were cut from captured output by EMA, so the first 404 observation is not recorded.) aem.live HTTP 404. Audit: indexer 'content: deleted /us/en/magazine/arctic-surfing' 16:40:14 IST; sitemap (system) 16:40:15 IST. Page no longer in live query-index.json. | Passed
42 | 19/10/2026, 16:46:18 IST | Wrap-up | User | Decisions | Final read-only snapshot: approved. Crontab: leave as is (6 past rows). Test pages: keep published. | Approved
43 | 19/10/2026, 16:47:11 IST | Wrap-up | EMA | Final read-only status snapshot (16:46:18 IST) | 28 docs vs baseline: exactly 6 changed (beervana-portland, tahoe-skiing, guide-la-skateparks, san-diego-surf, ski-touring, western-australia: live 404 -> 200). 22 unchanged incl. napa-wine-tasting (still 404, T2) and arctic-surfing (back to 404, T5). All 11 originally-published pages: live.lastModified unchanged. 11 pages now unpublished. | OK
44 | 19/10/2026, 16:47:17 IST | Wrap-up | EMA | Final summary written | Final Summary tab completed; report delivered to user. | Done

## Scheduling Changes
Logged At (IST) | Task | Page(s) | Change Type | Original Time (IST / UTC) | Updated Time (IST / UTC) | Crontab Entry (when ¦ command) | Status | Notes
19/10/2026, 15:46:24 IST | T1 | /us/en/adventures/beervana-portland | New schedule (publish) | 16:00 IST / 10:30 UTC | - | at 10:30 am on the 19th day of October in 2026 ¦ publish /us/en/adventures/beervana-portland | Active (activated 15:46 IST) | Crontab v1
19/10/2026, 15:47:29 IST | T2 | /us/en/adventures/napa-wine-tasting | New schedule (publish) | 16:10 IST / 10:40 UTC | - | at 10:40 am on the 19th day of October in 2026 ¦ publish /us/en/adventures/napa-wine-tasting | Active (activated 15:47 IST) | Crontab v2
19/10/2026, 15:47:29 IST | T3 | /us/en/adventures/tahoe-skiing | New schedule (publish) | 16:10 IST / 10:40 UTC | - | at 10:40 am on the 19th day of October in 2026 ¦ publish /us/en/adventures/tahoe-skiing | Active (activated 15:47 IST) | Crontab v2
19/10/2026, 15:51:24 IST | T2 | /us/en/adventures/napa-wine-tasting | Cancellation | 16:10 IST / 10:40 UTC | Cancelled (row removed) | (removed) at 10:40 am on the 19th day of October in 2026 ¦ publish /us/en/adventures/napa-wine-tasting | Cancelled (activated 15:51 IST) | Crontab v3; done after 15:50 IST tick
19/10/2026, 15:51:24 IST | T3 | /us/en/adventures/tahoe-skiing | Reschedule | 16:10 IST / 10:40 UTC | 16:20 IST / 10:50 UTC | at 10:50 am on the 19th day of October in 2026 ¦ publish /us/en/adventures/tahoe-skiing | Active (activated 15:51 IST) | Crontab v3; done after 15:50 IST tick
19/10/2026, 15:53:43 IST | T5 | /us/en/magazine/arctic-surfing | New schedule (publish) | 16:25 IST / 10:55 UTC | - | at 10:55 am on the 19th day of October in 2026 ¦ publish /us/en/magazine/arctic-surfing | Active (activated 15:53 IST) | Crontab v4
19/10/2026, 15:53:43 IST | T5 | /us/en/magazine/arctic-surfing | New schedule (unpublish) | 16:40 IST / 11:10 UTC | - | at 11:10 am on the 19th day of October in 2026 ¦ unpublish /us/en/magazine/arctic-surfing | Active (activated 15:53 IST) | Crontab v4
19/10/2026, 15:55:46 IST | T4 | /us/en/magazine/guide-la-skateparks, /san-diego-surf, /ski-touring, /western-australia | New schedule (bulk publish) | 16:25 IST / 10:55 UTC | - | at 10:55 am on the 19th day of October in 2026 ¦ publish …/guide-la-skateparks\npublish …/san-diego-surf\npublish …/ski-touring\npublish …/western-australia | Active (activated 15:55 IST) | Crontab v5; single cell with 4 commands
19/10/2026, 16:01:23 IST | T1 | /us/en/adventures/beervana-portland | Executed | 16:00 IST / 10:30 UTC | - | at 10:30 am … ¦ publish /us/en/adventures/beervana-portland | Executed 16:00:04 IST | Row left in sheet (one-time, past date — will not re-run)
19/10/2026, 16:13:46 IST | T2 | /us/en/adventures/napa-wine-tasting | Verification | 16:10 IST / 10:40 UTC | Cancelled | (row absent) | Did NOT execute — confirmed 16:13 IST | Cancellation effective
19/10/2026, 16:13:47 IST | T3 | /us/en/adventures/tahoe-skiing | Verification (original time) | 16:10 IST / 10:40 UTC | 16:20 IST / 10:50 UTC | at 10:50 am … ¦ publish /us/en/adventures/tahoe-skiing | Did NOT execute at original time — confirmed 16:13 IST | Awaiting 16:20 IST
19/10/2026, 16:21:01 IST | T3 | /us/en/adventures/tahoe-skiing | Executed (updated time) | 16:10 IST / 10:40 UTC | 16:20 IST / 10:50 UTC | at 10:50 am … ¦ publish /us/en/adventures/tahoe-skiing | Executed 16:20:04 IST | Ran at updated time only
19/10/2026, 16:26:20 IST | T4 | 4 magazine pages | Executed (bulk) | 16:25 IST / 10:55 UTC | - | multi-command row | Executed 16:25:04-16:25:06 IST (4/4)
19/10/2026, 16:26:21 IST | T5 | /us/en/magazine/arctic-surfing | Executed (publish) | 16:25 IST / 10:55 UTC | - | at 10:55 am … ¦ publish /us/en/magazine/arctic-surfing | Executed 16:25:04 IST | Unpublish pending 16:40 IST
19/10/2026, 16:42:44 IST | T5 | /us/en/magazine/arctic-surfing | Executed (unpublish) | 16:40 IST / 11:10 UTC | - | at 11:10 am … ¦ unpublish /us/en/magazine/arctic-surfing | Executed on 16:40 IST tick (index deletion 16:40:14 IST)

## Integrations
System / Service | Endpoint / Tool | Purpose | Access | Observations | Integration Issues
Document Authoring (DA) Source API | https://admin.da.live/list¦source/araji-adobe/bv-poc-wknd-aln/... | List pages; create/update the scheduler crontab sheet at /.helix/crontab | Accessible (200) | Listed 28 documents. Created /.helix/crontab.json 15:46 IST (HTTP 200). | 1st upload attempt returned no response (local tool error); retry succeeded.
AEM Admin — Status API | GET https://admin.hlx.page/status/ARAJI-ADOBE/bv-poc-wknd-aln/main/{path} | Read preview/live status + last-modified per page (verification) | Accessible (200) | Used for the initial page inventory snapshot.
AEM Admin — Preview API | POST https://admin.hlx.page/preview/ARAJI-ADOBE/bv-poc-wknd-aln/main/.helix/crontab.json | Activate the crontab sheet (scheduler reads the previewed version) | Accessible (200) | Crontab activated 5 times (15:46, 15:47, 15:51, 15:53, 15:55 IST), all HTTP 200, no x-error.
AEM Scheduler (background crontab runner) | Reads previewed /.helix/crontab; runs every 5 min (:00, :05, ...); times in UTC | Executes publish / unpublish commands at the scheduled times | Indirect only | All 6 scheduled actions ran on their tick: T1 16:00:04, T3 16:20:04 (not at original 16:10), T4 16:25:04-06 (4 pages, one multi-command cell), T5 publish 16:25:04, T5 unpublish 16:40 tick (index deletion 16:40:14). Cancelled T2 row did not run. | No scheduler-attributed entry in the audit log (O1).
AEM Admin — Audit Log API | GET https://admin.hlx.page/log/ARAJI-ADOBE/bv-poc-wknd-aln/main?since=… | Evidence of when publish/unpublish actually ran and by whom | Accessible (200) | Records crontab previews (araji@adobe.com) and downstream indexer/sitemap/query-index entries (user: system) ~10 s after each scheduled publish/unpublish (content added / content deleted). | No route=live/unpublish entry for scheduler runs (O1); ingestion delay ~1 min (O2).
AEM Delivery — live CDN | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/{path} | End-user check that page is live / gone | Public HTTP | aem.live returned 200 immediately after each publish and 404 after unpublish/cancel; no stale-cache issues observed.
AEM Delivery — preview | https://main--bv-poc-wknd-aln--araji-adobe.aem.page/{path} | Reference for "latest content" comparison | Public HTTP | Used as reference; live .plain.html byte-identical to preview for all 7 publishes.
AEM Admin — Snapshot / Jobs APIs | GET admin.hlx.page/snapshot/… , /job/…/publish | Checked for pre-existing schedules/jobs | Accessible (200) | No snapshots, no publish jobs at baseline. Not used for this test.

## Issues & Limitations
ID | Task | Type | Description | Impact | Workaround / Mitigation | Status
L1 | All | Limitation | The scheduler is driven by a single crontab sheet at /.helix/crontab. It does not exist yet and must be created (state-changing; needs approval). | All tasks depend on it. | Sheet created 15:46 IST with approval; 5 versions (v1-v5) activated, all HTTP 200. Left in place per user (6 past one-time rows; will not re-run). | Closed
L2 | All | Limitation | Scheduler runs only every 5 minutes (:00/:05/…) and crontab times are UTC. A job whose time is before the next tick after activation is skipped. | Times must be 5-minute aligned with a lead time; execution can lag a few minutes. | All times 5-min aligned; every job executed 4-6 s after its tick (16:00:04, 16:20:04, 16:25:04-06, 16:40 tick). | Closed
L3 | All | Limitation | No API to list jobs queued by the scheduler. | "Schedule saved" can only be verified as: sheet content + successful activation (preview 200). Actual registration is Not Verified until execution. | Verify via status + audit log after each tick. | Accepted
L4 | All | EMA limitation | EMA cannot wake up on its own between chat turns to monitor scheduled events. | Verification happens only when the user resumes the chat (EMA can wait in-session up to ~10 min per check). | User approved each check; EMA waited in-session (sleep + 20 s polling). No unattended monitoring. | Accepted
L5 | All | Risk | All tests share one crontab sheet; a syntax error disables every scheduled job in it. | Parallel tests share failure risk. | No syntax errors in any of the 5 activations. | Closed
L6 | All | Constraint | Per standing user instruction, EMA never publishes directly (no /live calls). All publish/unpublish actions go through the scheduler only. | Retests also require scheduling. | — | Info
O1 | T1 | Observation | Scheduler-executed publish is not recorded as a route=live entry in the audit log; only the downstream indexer (content added) and sitemap/query-index (user: system) entries appear. | Who/what triggered the publish is inferred, not explicitly attributed to the scheduler in the log. | Use live.lastModified from Status API + indexer entry as evidence; EMA made no direct /live calls. | Info
O2 | T3 | Observation | Audit-log entries surface with a delay: T3 indexer entry timestamped 16:20:35 IST was not returned by a query at 16:20:49 IST but was present by 16:25. | Audit log must be re-queried a minute or more after a run. | Re-query later; Status API is the immediate source. | Resolved
O3 | T5 | Limitation | After unpublish, the Status API returns live 404 with no timestamp, so the exact unpublish second cannot be read directly. | Unpublish time is evidenced by the indexer deletion entry (16:40:14 IST) rather than a live timestamp. | Use audit-log indexer "content: deleted" entry + polling. | Info
E1 | T5 | EMA error | EMA trimmed captured poll output (tail), losing poll lines between 16:39:30 and 16:40:53 IST. | First observed 404 time recorded as 16:40:53 IST rather than the actual first poll after the tick. | Indexer deletion entry (16:40:14 IST) used as primary evidence. | Info
L7 | All | Limitation | Activation (preview) response does not echo the parsed schedule or confirm syntax validity beyond HTTP 200 / absence of x-error; /.helix/crontab.json is not publicly readable. | Parse correctness is only proven when the job runs. | Verify by execution evidence (as done). | Accepted

## Final Summary
Item | Value
Report | AEM Edge Delivery — Scheduler (crontab) End-to-End Test
Site | araji-adobe / bv-poc-wknd-aln (branch main) — DA content source
Timezone | IST (UTC+05:30) — crontab entries are written in UTC
Log created | 19/10/2026, 15:29:48 IST
Last updated | 19/10/2026, 16:47:17 IST
Testing window (planned) | Proposed: 19 Oct 2026, ~15:40 – 17:10 IST (awaiting approval)
Total tasks | 5
Passed | 5
Failed | 0
Blocked | 0
Pending | 0
Notes | Testing complete. All 5 tasks executed and Passed. Actual window: 15:32 IST (plan approval) – 16:46 IST (final snapshot) ≈ 74 min.
Publishing verification | 7 scheduled publishes (T1, T3, T4×4, T5) — 7/7 live at expected tick; content identical to preview for all 7.
Unpublishing verification | T5 unpublish on 16:40 IST tick — Passed (index deletion 16:40:14 IST; live 404). Exact unpublish second Not Verified (O3).
Scheduling / rescheduling accuracy | All executions 4–6 s after the scheduled 5-min tick. T3 ran only at the updated time (16:20), not the original (16:10). T2 cancellation effective (still unpublished at 16:46).
Bulk publishing | T4: 4/4 pages published 16:25:04–16:25:06 IST from one multi-command crontab cell.
Integration issues | O1: scheduler runs not attributed in audit log (only indexer/sitemap side effects). O2: audit-log ingestion delay ~1 min (resolved). L7: activation gives no parse feedback.
EMA limitations | Cannot monitor unattended between chat turns (L4); cannot list scheduler queue (L3); E1: EMA trimmed some poll output during T5.
Manual interventions | None required beyond user approvals at each step.
Final site state | 6 test pages now live (kept per user). napa-wine-tasting and arctic-surfing unpublished. Crontab left with 6 past one-time rows (per user). 11 pages remain unpublished.
Follow-ups / risks | (1) Past rows remain in crontab — clear when real schedules are added to avoid confusion. (2) Rows without "in <year>" repeat yearly. (3) A syntax error in the shared sheet disables all schedules — validate after edits. (4) Only preview → publish was tested; pages edited after preview publish their previewed (not latest DA) content unless a preview command is added.

## Page Inventory (Initial)
Page Path | Live URL | Preview Status | Preview Last Modified (IST) | Live Status | Live Last Modified (IST) | State at Snapshot
/footer | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/footer | 200 | 16/10/2026, 15:35:44 IST | 200 | 16/10/2026, 15:34:20 IST | Published
/nav | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/nav | 200 | 16/10/2026, 15:35:42 IST | 200 | 16/10/2026, 15:34:17 IST | Published
/us/en/about-us | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/about-us | 200 | 16/10/2026, 15:35:48 IST | 200 | 16/10/2026, 15:34:31 IST | Published
/us/en/adventures/bali-surf-camp | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/bali-surf-camp | 200 | 16/10/2026, 15:36:12 IST | 200 | 16/10/2026, 15:24:57 IST | Published
/us/en/adventures/beervana-portland | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/beervana-portland | 200 | 16/10/2026, 15:36:00 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/climbing-new-zealand | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/climbing-new-zealand | 200 | 16/10/2026, 15:36:03 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/colorado-rock-climbing | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/colorado-rock-climbing | 200 | 16/10/2026, 15:35:53 IST | 200 | 16/10/2026, 15:34:43 IST | Published
/us/en/adventures/cycling-southern-utah | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/cycling-southern-utah | 200 | 16/10/2026, 15:35:52 IST | 200 | 16/10/2026, 15:34:40 IST | Published
/us/en/adventures/cycling-tuscany | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/cycling-tuscany | 200 | 16/10/2026, 15:35:51 IST | 200 | 16/10/2026, 15:34:37 IST | Published
/us/en/adventures/downhill-skiing-wyoming | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/downhill-skiing-wyoming | 200 | 16/10/2026, 15:36:01 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/gastronomic-marais-tour | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/gastronomic-marais-tour | 200 | 16/10/2026, 15:35:58 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/napa-wine-tasting | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/napa-wine-tasting | 200 | 16/10/2026, 15:35:56 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/riverside-camping-australia | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/riverside-camping-australia | 200 | 16/10/2026, 15:36:07 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/ski-touring-mont-blanc | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/ski-touring-mont-blanc | 200 | 16/10/2026, 15:36:19 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/surf-camp-costa-rica | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/surf-camp-costa-rica | 200 | 16/10/2026, 15:36:11 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/tahoe-skiing | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/tahoe-skiing | 200 | 16/10/2026, 15:36:05 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/west-coast-cycling | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/west-coast-cycling | 200 | 16/10/2026, 15:35:54 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/whistler-mountain-biking | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/whistler-mountain-biking | 200 | 16/10/2026, 15:36:09 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures/yosemite-backpacking | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures/yosemite-backpacking | 200 | 16/10/2026, 15:36:13 IST | 404 | - | Unpublished (previewed only)
/us/en/adventures | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/adventures | 200 | 16/10/2026, 15:35:46 IST | 200 | 16/10/2026, 15:34:25 IST | Published
/us/en/faqs | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/faqs | 200 | 16/10/2026, 15:35:49 IST | 200 | 16/10/2026, 15:34:33 IST | Published
/us/en/magazine/arctic-surfing | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/arctic-surfing | 200 | 16/10/2026, 15:36:21 IST | 404 | - | Unpublished (previewed only)
/us/en/magazine/guide-la-skateparks | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/guide-la-skateparks | 200 | 16/10/2026, 15:36:15 IST | 404 | - | Unpublished (previewed only)
/us/en/magazine/san-diego-surf | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/san-diego-surf | 200 | 16/10/2026, 15:36:17 IST | 404 | - | Unpublished (previewed only)
/us/en/magazine/ski-touring | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/ski-touring | 200 | 16/10/2026, 15:36:22 IST | 404 | - | Unpublished (previewed only)
/us/en/magazine/western-australia | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine/western-australia | 200 | 16/10/2026, 15:36:24 IST | 404 | - | Unpublished (previewed only)
/us/en/magazine | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en/magazine | 200 | 16/10/2026, 15:35:47 IST | 200 | 16/10/2026, 15:34:28 IST | Published
/us/en | https://main--bv-poc-wknd-aln--araji-adobe.aem.live/us/en | 200 | 16/10/2026, 15:35:45 IST | 200 | 16/10/2026, 15:34:23 IST | Published